## Training Plan
Training Plan
List all training or learning activities your project will need. These can be formal sessions, quick demos, or simple how-to guides. Start with the biggest impacts from your Impact Analysis.
Audience / Role | Training Topic / Focus | Format / Method | Estimated Duration | Timing / Phase | Owner / Facilitator | Materials Needed | Follow-Up / Reinforcement
Who needs this training? (e.g., Finance Clerks, Supervisors) | What skill or process will they learn? | Dropdown: Instructor-led, eLearning, Quick Demo, Job Aid, Email Tip Sheet | How long will it take? (minutes or hours) | When should it happen? (e.g., UAT, Go-Live, Post-Launch) | Who will deliver or coordinate it? | Any supporting docs, slides, or links. | How will you ensure they retain it?
💡 Quick Steps to Make It Stick
Quick Step | Purpose / Impact
Confirm each audience matches an impact group | Ensures you’re covering all who are affected.
Combine sessions when possible | Saves time and creates shared understanding.
Record short demos or walkthroughs | Allows people to revisit content later.
Ask for feedback after the first session | Helps refine and improve later training rounds.
Reinforce key behaviors in team meetings | Keeps adoption steady after go-live.
⚠️ Common Pitfalls & Pro Tips
Pitfall | Pro Tip to Avoid It
Not planning enough time to create, review, and approve content | Build time for drafting and internal review into your project schedule — training content almost always takes longer than expected.
Not identifying who will create and review materials | Assign clear roles early: content creator, SME reviewer, and final approver. Include them in your project roster.
Not involving the Training or LMS team early | As soon as you know your training milestones, alert your training/LMS team. They’ll help schedule sessions, upload content, and track completion. This is critical if you plan to use your e-learning system.
Assuming the vendor’s training materials will meet your needs | Review this Training Plan against the vendor’s content. Fill any gaps with in-house sessions or custom materials that reflect your company’s processes.